WMS selection toolkit · SET-04

# WMS implementation plan and go-live checklist

Most WMS project problems come not from the software but from unprepared data, incomplete testing and a rushed go-live. This plan is a framework to assess the vendor's plan and track your own side of the work.

# Project phases

Durations vary with scope, number of sites and integrations. Ask the vendor for a plan per phase with durations, deliverables and the resources expected from you.

| Phase | Key activities | Deliverable | Owner |
| --- | --- | --- | --- |
| 1. Mobilisation | Project team, governance, communication plan, risk log | Project charter | Customer + vendor |
| 2. Analysis and design | Process workshops, exceptions, location structure, labels, integration interfaces | Signed-off solution design (scope document) | Vendor, customer sign-off |
| 3. Configuration and build | System rules, reports, custom developments, integrations | Working system in the test environment | Vendor |
| 4. Testing | Unit, integration, user acceptance (UAT) and load tests | Signed UAT report, open defect list | Customer (UAT), vendor |
| 5. Data migration | Item master, locations, opening stock, open orders; trial loads | Validated data load | Customer (data), vendor (tools) |
| 6. Training | Key-user training, operator training, manuals | Training records | Vendor + key users |
| 7. Go-live | Go / no-go decision, stock count, cut-over, on-site support | Live system | Joint |
| 8. Hypercare | Intensive support, daily stand-ups, KPI tracking, closure | Project closure report | Joint |

# Customer-side responsibilities

☐  Appoint a project owner with decision authority and a near-full-time project manager.

☐  Name a key user for each main process (receiving, inventory, picking, shipping).

☐  Plan IT resources for ERP-side development and testing from the start.

☐  Start cleaning item master data (dimensions, weight, barcodes) at the start of the project.

☐  Have hardware (handhelds, printers, Wi-Fi coverage) ready on site before testing.

☐  Finish labels, location barcodes and rack labelling before go-live.

# Test plan

- User acceptance testing (UAT): real scenarios, real users and handhelds; use the demo scenarios (SET-02) as a starting point.

- End-to-end integration testing: the full flow from an order created in the ERP to shipment and invoicing.

- Load testing: system and network performance at your peak-day order volume.

- Rollback rehearsal: how to return to the old process if go-live fails.

# Go-live (go / no-go) checklist

Make the go-live decision against this list, not the calendar. Assign an owner and evidence to each item.

☐  UAT signed off; no open critical or high-priority defects.

☐  End-to-end integration tests passed; error monitoring and its owner are in place.

☐  Master data loaded and verified by sampling.

☐  Stock count plan for the opening balance and variance approval method ready.

☐  All users trained; user accounts and access rights set up.

☐  Handhelds, printers and Wi-Fi coverage tested on site.

☐  Location and item labels printed and applied.

☐  An hour-by-hour cut-over plan: ERP transaction freeze, last movements, count, opening.

☐  Customers and carriers informed about the cut-over; order intake adjusted if needed.

☐  Vendor team on site for the first week(s); support line and escalation path clear.

☐  Rollback plan and decision criteria written down.

# Hypercare

- Hold a short daily stand-up in the first weeks: open issues, shipping status, stock variances.

- Track the KPIs you measured before go-live (accuracy, productivity, lead time) weekly.

- Write down the exit criteria for hypercare in advance (e.g. no critical defects for a set period).

- At closure, record lessons learned and the next list of improvements.

This document is a general working template; it is not a substitute for legal, financial or technical advice. Adapt it to your circumstances.